## 2026
Quarter | Format | Event | Start Date | End Date | Location | Participation | Size | Budget | Target MQLs | Target SQLs | Target Deals | Target Pipeline | Target Closed won | Target Revenue | Target ROI | Attendees | MQLs | SQLs | Deals | Pipeline | Deals won | Revenue | Projected ROI X | Website | Description | City | Venue | Target Audience | Previous edition highlights | Sponsors | Agenda summary
Q1-2026 | Conference | Dunham Summit | 2026-01-06 | 2026-01-08 | Florida | Speaking | Small | 45000 | 30 | 13.5 | 1.89 | 948407.67 | 0.3969 | 81430.7823 | 80.96% | 35 | 30 | 12.6 | 0.504 | 252908.712 | 0.10584 | 21714.8753 | -51.74% | https://dcsummit.zohobackstage.com/DunhamSummit2026 | The Dunham Summit 2026 is an event focused on inspiring attendees, building relationships, and pr... | Lake Buena Vista |  | This event is designed for individuals seeking inspiration, strategic insight, and personal renewal to grow their impact and lead with confidence, particularly those involved in a visionary movement for a greater cause or His Kingdom. |  | No sponsor information was found on the page. | The agenda details for the Dunham Summit 2026 are not available on the provided webpage. The page indicates that more information will be shared soon.
Q1-2026 | PRAY Retreat | Agency Retreat | 2026-01-26 | 2026-01-28 | San Diego | Hosting | Small | 80000 | 18 | 75200 | 6768 | 272973744 | 4534.56 | 738725169.6 | 923306% | 18 | 18 | 16.92 | 1.5228 | 61419.0924 | 1.0203 | 166213.1632 | 107.8%
Q1-2026 | NRB | NRB International Christian Media Convention | 2026-02-17 | 2026-02-20 | Nashville, TN | Booth + Speaking | Large | 450000 | 655 | 307.85 | 43.099 | 4892124.391 | 21.1185 | 2885717.68 | 541.3% | 6000 | 655 | 307.85 | 43.099 | 4892124.391 | 21.1185 | 2885717.68 | 541.3% | nrbconvention.org | The NRB International Christian Media Convention is the world's largest gathering of Christian co... | Nashville | Gaylord Opryland Resort and Convention Center | The NRB International Christian Media Convention is the world's largest gathering of Christian communicators and ministry professionals. It is designed for individuals working in radio, TV, film, church media, digital marketing, and other media-related fields who aim to grow their ministry, church, or organization and effectively reach audiences with their message. | This field is not used in the final output schema. | The NRB 2026 convention lists the following sponsors: **Top-Level Sponsors:** * Gloo: Diamond Sponsor * Elijah Streams Ministry: Bronze Sponsor * Ignite America: Bronze Sponsor * Great American Pure Flix: Bronze Sponsor **Event/Area Sponsors:** * Apex Media: Club 44 Sponsorship * Turning Point: Club 44 Sponsorship, Press Center Sponsorship * Galcom International: Membership Meeting Sponsorship * Faithsearch Partners: Membership Meeting Sponsorship, Board Meeting Sponsorship * The Discovery Institute: Board Meeting Sponsorship * Douglas Shaw & Associates: NRB Board Meeting Sponsorship * Christians Engaged: Opening Session Sponsorship * IFJC: Breakfast to Honor Israel Sponsorship * Combat Antisemitism Movement: Breakfast to Honor Israel Sponsorship * Life Surge: Closing Gala Sponsorship * Sight & Sound: Media Awards Lunch Sponsorship * CHM: Media Leadership Dinner Sponsorship * Tithe.ly: Church Media Lab Sponsorship For the NRB 2025 convention, top-level sponsors included: * Gloo AI: Platinum Sponsor * Patriot Mobile: Silver Sponsor * Ignite America: Bronze Sponsor * Prime Video and Wonder Project: Bronze Sponsor Additionally, for the NRB 2025 'Breakfast to Honor Israel', co-sponsors were: * Combat Antisemitism Movement (CAM) * International Christian Embassy Jerusalem (ICEJ) * Magen David Adom | The NRB 2026 Convention features an Opening Session and over 50 Expert-Led Sessions. Key scheduled events include the Digital Ministry Conference on February 17th (8:00 AM - 5:00 PM), the TV Showcase on February 17th (1:00 PM - 3:00 PM), the Latino Media Summit on February 18th-19th (9:00 AM - 12:00 PM), the 53rd ICVM Crown Awards on February 18th (8:00 PM - 10:00 PM), and the Pitch-a-thon on February 20th (3:00 PM - 5:00 PM).
Q1-2026 | PRAY Mini Event | March Event 1 / TBD | 2026-03-01 | 2026-03-01 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q1-2026 | PRAY Mini Event | March Event 2 / TBD | 2026-03-19 | 2026-03-19 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q2-2026 | PRAY Mini Event | April Event 1 / TBD (NBA Playoff?) | 2026-04-19 | 2026-04-19 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q2-2026 | Conference | America Reads the Bible | 2026-04-20 | 2026-04-21 | D.C | TBD | Medium | 35000 | 70 | 31.5 | 4.41 | 2212951.23 | 0.9261 | 190005.1587 | 442.9% |  | 70 | 29.4 | 1.176 | 590120.328 | 0.24696 | 50668.0423 | 44.77% | https://www.americareadsthebible.com/inperson | America Reads the Bible is a week-long national gathering scheduled for April 18-25, 2026, in Was... | Washington, D.C. | Museum of the Bible | This event is for anyone curious about Scripture, including pastors, students, parents, and business leaders. Families are also encouraged to attend this week-long, continuous Bible-reading event. | No information was found regarding a previous year's edition of the 'America Reads the Bible' event. | The 'Attend live' page (https://www.americareadsthebible.com/inperson) does not directly list sponsors. However, partner information is available on the 'Our Partners' page and the main website. The identified sponsors and their tiers are as follows: **Host Ministry:** - Christians Engaged **Production & Distribution Partner:** - CandyRock Entertainment - Christ Over Career **Discipleship Partners:** - CBN - Museum of the Bible - Waterstone - WallBuilders - Whitaker House - Allen Jackson - Jack Graham - Family Policy Alliance - Time to Revive - NHCLC - AWMI - FRC **Celebration Partner:** - Pray.com **Prayer Ministry Partner:** - Her Voice MVMT **Religious Liberty Partner:** - First Liberty Institute **Hospitality Partner:** - Salt and Light Council **Partner:** - Pureflix | The America Reads the Bible event features an Opening Celebration on April 18, 2026, with a reception and a 90-minute program. The Main Event runs from April 19-25, 2026, at the Museum of the Bible, offering continuous Scripture reading in the World Stage Theatre, access to a private art gallery, and opportunities to connect with Discipleship Partners.
Q2-2026 | PRAY Retreat | Pastor Retreat (Partnerships) 1 of 2 | 2026-04-22 | 2026-04-24 |  | Hosting | Small | 80000 | 18 | 75200 | 6768 | 272973744 | 4534.56 | 738725169.6 | 923306% | 18 | 18 | 16.92 | 1.5228 | 61419.0924 | 1.0203 | 166213.1632 | 107.8% | TBD
Q2-2026 | Conference | MegaMetro (Senior Pastors) | 2026-04-26 | 2026-04-28 | Boston, MA | TBD | Medium | 34850 | 64 | 28.8 | 4.032 | 2023269.696 | 0.84672 | 173719.0022 | 398.5% |  | 64 | 26.88 | 1.0752 | 539538.5856 | 0.22579 | 46325.0673 | 32.93% | megametro.org | MEGA METRO is a conference designed for church leaders and pastors, scheduled to take place in Bo... | Boston | Four Seasons Hotel Boston | Mega Metro 2026 is a leadership conference designed to provide encouragement, personal growth, and equip attendees to better serve and lead their churches. | No specific highlights, testimonials, or success metrics for the 2024 event were found on megametro.org. The website promotes the 2026 event and includes a '2025 Recap' section that contains only images. | ARC, Gloo, Ministry Brands | No agenda or schedule section was found on the provided page.
Q2-2026 | Conference | Outcomes Conference (CLA) | 2026-04-28 | 2026-04-30 | Dallas, TX | Booth + Speaking | Large | 34850 | 20 | 9 | 1.26 | 632271.78 | 0.2646 | 54287.1882 | 55.77% | 1000 | 20 | 8.4 | 0.336 | 168605.808 | 0.07056 | 14476.5835 | -58.46% | https://christianleadershipalliance.org/outcomes-conference/ | The Outcomes Conference, hosted by the Christian Leadership Alliance (CLA), is an annual event de... | Dallas | Hyatt Regency DFW International Airport | The Outcomes Conference is designed for Christian nonprofit professionals and leaders across all organizational levels, including executives, board members, and staff, who aim to enhance their leadership skills, transform their missions, and increase their kingdom impact within churches and ministries. | The Outcomes Conference 2024 was held from April 9-11 in Jacksonville, Florida, under the theme 'Therefore'. The event focused on personal and professional leadership development, featuring prominent speakers such as Dr. Justin A. Irving (whose book 'Healthy Leadership for Thriving Organizations' was named the Book of the Year), Dr. Courtney Veasey, Dr. Rob McKenna, Faith Eury Cho, Pastor John K. Jenkins Sr., Marvin Campbell, and Rev. Dr. Gabriel Salguero. The conference also included 'Experience Guides' like Ayanda Khumalo, Season Bowers, and Dr. Naomi Cramer Overton, and highlighted the movie screening of 'THE FORGE'. No specific numerical success metrics or direct testimonials about the conference experience were found in the provided search results. | The following organizations are listed as sponsors for the Outcomes Conference 2026: **Premier:** * Cru * FaithSearch Partners * The Salvation Army USA **Presidential:** * Americas Christian CU **Executive:** * Douglass Shaw & Associates * NavPress **Advocate:** * Best Christian Workplaces * ECFA * Masterworks **Supporting:** * Barnabas Foundation * BMO * CapinCrouse * Compassion * Gallagher * Joni and Friends * Reaching Souls * SpreadTruth * World Vision | The JSON object contains the extracted agenda information, including the source URL, confirmation of finding an agenda section, a summary of key agenda items, and relevant notes.
Q2-2026 | American Prays | America Prays National Mall Event | 2026-05-18 | 2026-05-18 | Washington D.C. | TBD | Large | 50000 | [6 empty] | -100% | [7 empty] | TBD | https://america250.org/event/national-summit-on-civic-education/?view=list&date=next6Months&inPerson=true | The National Summit on Civic Education convenes civic educators, thought leaders, funders, and le... | Philadelphia | Independence Mall | The 2026 National Summit on Civic Education will bring together civic educators, thought leaders, funders, and business and civil society leaders to discuss the Declaration of Independence and its relevance in American education. | The 2024 National Summit on Civic Education, themed 'Educators and Innovators: Our Civics Moment,' focused on exploring bipartisan strategies for depolarizing classrooms and fostering open dialogue. A related dinner featured a conversation on reclaiming truth in higher education, and a '2024 Summit Magazine' titled 'Can Civic Education Save Our Institutions?' was produced. | Lead Sponsor (2026 Summit): The Teagle Foundation. Other Sponsors listed under the 2026 Summit Sponsors include Amazon, Oracle, Lockheed Martin, UFC, Coinbase, Palantir, Walmart, Domino Sugar, Exiger, Florida Crystals, General Mills, Goldman Sachs, Intuit, Kraft Heinz, Leidos, The Coca-Cola Company, Chrysler, Dodge, Jeep® , Ram Brands, Phorm Energy, ScottsMiracle-Gro, and With Honor. These names are shown as part of the event’s sponsor sections on the National Summit on Civic Education pages. | The provided URL describes the National Summit on Civic Education but does not contain a detailed agenda. However, based on information from a linked page, key highlights of the event include: - The summit is scheduled for May 18-19, 2026, on Philadelphia's historic Independence Mall. - Highlights include a naturalization ceremony for thirteen new U.S. citizens. - The event will feature lunch with renowned columnist Peggy Noonan. - A keynote address from a distinguished national figure will be presented. - Shark-tank style presentations on catalytic projects in civic education are planned.
Q3-2026 | Conference | BCI (Black christian influencers) | 2026-06-19 | 2026-06-20 | Atlanta | Sponsor Only | Medium | 15000 | 20 | 9 | 1.26 | 632271.78 | 0.2646 | 54287.1882 | 261.9% |  | 20 | 8.4 | 0.336 | 168605.808 | 0.07056 | 14476.5835 | -3.489% | https://bciconference.org/
Q2-2026 | PRAY Mini Event | May Event 1 / TBD (Baseball?) | 2026-05-01 | 2026-05-01 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q2-2026 | PRAY event | PRAY Event - America Prays 250 | 2026-06-20 | 2026-06-20 |  | Hosting | Large | 375000 | [6 empty] | -100% |  | 600 | [5 empty] | -100%
Q2-2026 | PRAY Mini Event | June Event / TBD (Baseball?) | 2026-06-03 | 2026-06-03 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 18 | 18 | 16.92 | 1.5228 | 61419.0924 | 1.0203 | 166213.1632 | 454% | TBD
Q3-2026 | PRAY Mini Event | SBC (VIP owned Event) | 2026-06-06 | 2026-06-08 | Orlando, FL | Hosting | Small | 32200 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 51.55% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -26.38% | https://www.sbcpc.net/ | [5 empty] | PRAY.COM (owned event), Lifeway, NAMB
Q2-2026 | PRAY Retreat | Pastor Retreat (Partnerships) 2 of 2 | 2026-06-24 | 2026-06-26 |  | Hosting | Small | 80000 | 18 | 75200 | 6768 | 272973744 | 4534.56 | 738725169.6 | 923306% | 18 | 18 | 16.92 | 1.5228 | 61419.0924 | 1.0203 | 166213.1632 | 107.8% | TBD
Q3-2026 | PRAY Mini Event | Q3 Sporting Event | 2026-07-31 | 2026-07-31 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q3-2026 | PRAY Mini Event | Q3 Sporting Event | 2026-09-01 | 2026-09-01 |  | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98%
Q4-2026 | Conference | Family Reunion | 2026-10-27 | 2026-10-27 | TBD | TBD | Small | 10600 | 20 | 9 | 1.26 | 632271.78 | 0.2646 | 54287.1882 | 412.1% |  | 20 | 8.4 | 0.336 | 168605.808 | 0.07056 | 14476.5835 | 36.57% | TBD | [5 empty] | TBD — typically denominational sponsors
Q4-2026 | Conference | RockRMS Conference | 2026-11-03 | November 3-5 | Phoenix, AZ | TBD | Medium | 20900 | 64 | 28.8 | 4.032 | 2023269.696 | 0.84672 | 173719.0022 | 731.2% |  | 64 | 26.88 | 1.0752 | 539538.5856 | 0.22579 | 46325.0673 | 121.7% | https://rx.rockrms.com/ | The Rock RX event is dedicated to shaping the future of digital ministry, bringing together the R... | Phoenix | Phoenix Convention Center South Building | The Rock RMS Conference (RX) is designed for church leaders, ministry staff, IT professionals, developers, and administrators who use or are interested in Rock RMS. It provides insights into digital ministry, technology implementation, data management, and community engagement strategies for churches. | The Rock RX 2024 event featured several key highlights and successes. A new check-in system was introduced, utilizing NFC tokens, the Rock Mobile App, and wireless label printing. The Pre-Day event saw strong participation, with 74% of 662 attendees checking in, and included comedy and inspirational talks. The main conference days featured two keynote addresses, 101 breakout sessions, community lunches, and significant coffee consumption (over 300 gallons). The popularity of the 'Birds of a Feather' sessions indicated a need for larger venues in the future. The event was described as 'God's conference,' with an observed increase in first-time attendees from ministry roles. Discussions also covered upcoming features like version 17 (including adaptive messaging, LMS, and AI tools), the Obsidian UI framework, SEO strategies, and leveraging data for generosity. | RockRMS, TouchPoint, Pushpay, ChurchIT Network | The agenda for the Rock RX event has been successfully extracted and summarized.
Q4-2026 | PRAY Mini Event | November Sporting Event (Right Now Adjacent) | 2026-11-04 | 2026-11-06 | Dallas, TX | Hosting | Small | 30000 | 23 | 18.4 | 1.84 | 89792 | 0.828 | 48800 | 62.67% | 23 | 23 | 14.72 | 1.472 | 7360 | 0.48576 | 23705.088 | -20.98% | https://rightnowmedia.regfox.com/rightnow-conference-2026?t=tp | [5 empty] | TBD — typically denominational sponsors
Ongoing | Travels | AE Travel (2 times a month) |  |  |  | TBD | Small | TBD | [14 empty] | TBD
Ongoing | Travels | LS Travel (1 time a month) |  |  |  | TBD | Small | TBD | [14 empty] | TBD

## 1️⃣ TEMPLATE - HOSTED
Phase | Pillar | Category | Deliverable | Checklist (Execution Tasks) | Start Timeline | Start Date | Due Timeline | Due Date | Owner
Pre-Event | Mission Clarity | Strategy | Event purpose & primary business objective approved | Draft event purpose statement (Event Lead) Align objective to revenue + ministry goals (RevOps) Exec review & revisions (Exec Sponsor) Final approval recorded (Event Lead) | T-135 |  | T-120 |  | Event Lead
Pre-Event | Mission Clarity | Strategy | Quantified success targets set (attendees, meetings, deals) | Define attendee target (Marketing Ops) Calculate meeting target using 15.4% baseline (RevOps) Define deal target using 41.8% / 76.8% benchmarks (RevOps) Leadership approval recorded (Exec Sponsor) | T-135 |  | T-120 |  | RevOps
Pre-Event | Mission Clarity | Finance | Budget and ROI threshold approved | Draft event budget (Finance) Model ROI scenarios (RevOps) Review spend vs benchmarks (Finance) Final approval logged (Exec Sponsor) | T-135 |  | T-120 |  | Finance
Pre-Event | Mission Clarity | Brand | Faith & brand integrity guardrails documented | Review host/event alignment (Brand) Define faith non-negotiables (Ministry) Approve messaging boundaries (Brand) Guardrails archived (Event Lead) | T-135 |  | T-120 |  | Brand / Ministry
Pre-Event | Thematic Foundation | Creative | Spiritually grounded event theme approved | Draft theme concepts (Marketing) Validate spiritual alignment (Ministry) Select final theme (Marketing Lead) Approval recorded (Event Lead) | T-105 |  | T-90 |  | Marketing
Pre-Event | Thematic Foundation | Creative | Visual identity system finalized | Define color palette & typography (Creative) Create sample assets (Creative) Brand compliance review (Brand) Final lock (Marketing Lead) | T-90 |  | T-75 |  | Creative
Pre-Event | Thematic Foundation | Messaging | Messaging framework aligned to audience | Draft core narrative (Content) Map messaging to ICP personas (Growth) Align with sales language (Sales) Final approval (Marketing Lead) | T-90 |  | T-75 |  | Content
Pre-Event | Audience Architecture | Audience | ICP-defined attendee list finalized | Define ICP criteria (RevOps) Pull target attendee list (Marketing Ops) Remove non-qualified segments (Sales) Final list approved (Event Lead) | T-105 |  | T-90 |  | Marketing Ops
Pre-Event | Audience Architecture | Audience | Invitation & qualification strategy approved | Define invite channels (Growth) Define qualification gates (Sales Ops) Align CTA to success targets (RevOps) Approval recorded (Event Lead) | T-105 |  | T-90 |  | Growth
Pre-Event | Audience Architecture | Policy | Plus-one policy defined | Define eligibility rules (Event Lead) Assess capacity impact (Ops) Executive approval (Exec Sponsor) Policy documented (Event Lead) | T-90 |  | T-75 |  | Event Lead
Pre-Event | Experience Design | Journey | End-to-end attendee journey documented | Map pre-event journey (Experience Design) Map on-site moments (Ministry) Map post-event follow-up (Lifecycle) Journey review completed (Event Lead) | T-75 |  | T-60 |  | Experience Design
Pre-Event | Experience Design | Marketing | Registration + email sequences live | Define CTA & form fields (Growth) Write registration page & emails (Content) Design page (Creative) Build & QA in platform (Growth Ops) | T-75 |  | T-60 |  | Growth
During | Experience Design | On-Site | On-site experience flow finalized | Draft run-of-show (Event Ops) Define prayer/spiritual moments (Ministry) Cross-team walkthrough (Event Lead) Final lock (Event Ops) | T-45 |  | T-30 |  | Event Ops
Post | Experience Design | Follow-Up | 90-day nurture plan activated | Define nurture stages (Lifecycle) Write follow-up content (Content) Configure HubSpot workflows (RevOps) Activate Day 1 post-event (Lifecycle) | T-30 |  | T+1 |  | Lifecycle
Pre-Event | Operational Excellence | Planning | Critical path & risk register approved | Identify dependencies (Ops) Log risks & mitigations (Ops) Review with functional leads (Event Lead) Approval recorded (Event Lead) | T-105 |  | T-90 |  | Ops
Pre-Event | Operational Excellence | Systems | Platforms configured (HubSpot, analytics) | Configure HubSpot properties (RevOps) Test registration → CRM sync (RevOps) Validate reporting dashboards (RevOps) Sign-off recorded (Event Lead) | T-60 |  | T-45 |  | RevOps
Pre/During | Operational Excellence | Staffing | Staffing plan & run-of-show locked | Assign on-site roles (Event Ops) Confirm availability (People Ops) Distribute run-of-show (Event Lead) Final confirmation (Event Ops) | T-45 |  | T-30 |  | Event Ops
Pre-Event | Team & Accountability | Governance | RACI finalized | Define owner per deliverable (Event Lead) Review with functional leads (Ops) Executive sign-off (Exec Sponsor) Archive RACI (Event Lead) | T-105 |  | T-90 |  | Event Lead
Pre-Event | Team & Accountability | Approvals | Strategic / Creative / Ops approvals complete | Strategic approval (Exec Sponsor) Creative approval (Marketing Lead) Operational approval (Ops Lead) Gate completion logged (Event Lead) | T-45 |  | T-30 |  | Exec Sponsor
Post | Team & Accountability | Reporting | 30/60/90-day performance report delivered | Collect funnel data (RevOps) Analyze vs baseline metrics (RevOps) Draft insights & learnings (Event Lead) Leadership readout delivered (Exec Sponsor) | T+1 |  | T+90 |  | RevOps

## 2️⃣ TEMPLATE - SPONSORSHIP
Phase | Pillar | Category | Deliverable | Tasks (Execution Checklist) | Start Timeline | Start Date | Due Timeline | Due Date | Owner
Pre-Event | Mission Clarity | Strategy | Sponsorship objective defined | Define sponsorship goal (visibility vs. pipeline) (Partnerships) Confirm strategic fit with PRAY.COM priorities (Event Lead) Align objective with expected outcomes (RevOps) Objective documented and approved (Partnerships Lead) | T-105 |  | T-90 |  | Partnerships
Pre-Event | Mission Clarity | Finance | Minimum ROI threshold approved | Estimate expected reach/impressions (Partnerships) Model ROI scenarios (RevOps) Review cost vs. benchmark performance (Finance) Finance approval recorded (Finance Lead) | T-105 |  | T-90 |  | Finance
Pre-Event | Mission Clarity | Brand | Faith alignment confirmed with host | Review host theology/content positioning (Brand) Confirm no conflicting sponsors or messaging (Brand) Escalate risks if needed (Event Lead) Faith alignment approved and logged (Brand) | T-105 |  | T-90 |  | Brand
Pre-Event | Thematic Foundation | Brand | PRAY.COM brand representation approved | Review sponsor entitlements (Marketing) Confirm logo usage guidelines (Brand) Approve placements and sizing (Marketing Lead) Approval documented (Event Lead) | T-90 |  | T-75 |  | Marketing
Pre-Event | Thematic Foundation | Messaging | Messaging adapted to host event tone | Review host messaging and audience tone (Content) Adapt PRAY.COM copy accordingly (Content) Brand compliance review (Brand) Final approval recorded (Marketing Lead) | T-90 |  | T-75 |  | Content
Pre-Event | Audience Architecture | Audience | Audience overlap validated (ICP match) | Review attendee demographics (Marketing Ops) Compare to PRAY.COM ICP criteria (RevOps) Flag gaps or misalignment (Event Lead) ICP match confirmed (Marketing Ops) | T-105 |  | T-90 |  | Marketing Ops
Pre-Event | Audience Architecture | Forecasting | Expected reach quantified | Collect sponsor-provided attendance data (Partnerships) Estimate impressions/exposure (Marketing) Document assumptions and limits (RevOps) Reach estimate approved (Partnerships Lead) | T-90 |  | T-75 |  | Partnerships
Pre-Event | Experience Design | Activation | Sponsorship activation plan finalized | Identify all PRAY.COM exposure moments (Partnerships) Confirm inclusions with host (Partnerships) Define any CTA or next step (Growth) Final activation plan approved (Partnerships Lead) | T-75 |  | T-60 |  | Partnerships
Pre-Event | Experience Design | CTA | CTA or lead capture defined | Decide if CTA is used (Growth) Select CTA type (URL, QR, email, etc.) (Growth) Confirm feasibility with host (Partnerships) CTA documented and approved (Growth Lead) | T-60 |  | T-45 |  | Growth
Pre / Post | Experience Design | Access | Pre- or post-event touchpoint secured | Confirm email/list or social inclusion (Partnerships) Confirm timing and copy requirements (Content) Secure written confirmation from host (Partnerships) Touchpoint logged (Event Lead) | T-60 |  | T-45 |  | Partnerships
Pre-Event | Operational Excellence | Assets | Sponsorship assets delivered | Collect asset specs from host (Creative) Prepare logos or creative assets (Creative) Deliver assets by deadline (Creative) Delivery confirmed (Event Lead) | T-45 |  | T-30 |  | Creative
Pre-Event | Operational Excellence | Tracking | Attribution & tracking confirmed | Define attribution approach (RevOps) Set up tracking links if applicable (RevOps) Validate reporting method (RevOps) Tracking sign-off recorded (RevOps Lead) | T-45 |  | T-30 |  | RevOps
Pre-Event | Team & Accountability | Ownership | Single sponsorship owner assigned | Assign sponsorship owner (Partnerships Lead) Confirm decision authority (Event Lead) Communicate ownership to team (Ops) Owner recorded in system (Event Lead) | T-105 |  | T-90 |  | Partnerships Lead
Post | Team & Accountability | Reporting | Post-event ROI summary delivered | Collect reach + activation data (Partnerships Ops) Attribute impact where possible (RevOps) Draft ROI summary (RevOps) Leadership review delivered (Exec Sponsor) | T+1 |  | T+30 |  | RevOps

## 3️⃣ TEMPLATE - BOOTH
Phase | Pillar | Category | Deliverable | Tasks (Execution Checklist) | Start Timeline | Start Date | Due Timeline | Due Date | Owner | Event date
Pre-Event | Mission Clarity | Strategy | Primary objective defined | Define primary goal (meetings, partnerships, pipeline) (Partnerships) Confirm alignment with event format and audience (Event Lead) Validate objective against historical benchmarks (RevOps) Objective documented and approved (Partnerships Lead) | T-135 |  | T-120 |  | Partnerships
Pre-Event | Mission Clarity | Metrics | Quantified meeting & deal targets set | Calculate meeting target using 15.4% baseline (RevOps) Translate meetings to deal target using 41.8% benchmark (RevOps) Define success threshold (RevOps) Leadership approval recorded (Exec Sponsor) | T-135 |  | T-120 |  | RevOps
Pre-Event | Mission Clarity | Content | Speaking success criteria & CTA defined | Define desired audience action (Content) Select CTA (booking, demo, follow-up) (Growth) Map CTA to post-event path (Lifecycle) Success criteria approved (Content Lead) | T-105 |  | T-90 |  | Content Lead
Pre-Event | Mission Clarity | Brand | Faith & message alignment approved | Review event theology and host messaging (Brand) Approve booth + stage messaging boundaries (Brand) Escalate any conflicts (Event Lead) Approval documented (Brand) | T-105 |  | T-90 |  | Brand
Pre-Event | Thematic Foundation | Creative | Booth & stage messaging aligned | Draft booth headline and stage narrative (Marketing) Align messaging to event theme (Marketing) Brand and ministry review (Brand / Ministry) Final messaging approved (Marketing Lead) | T-90 |  | T-75 |  | Marketing
Pre-Event | Thematic Foundation | Assets | Booth visuals, slides, handouts approved | Design booth graphics (Creative) Create slide deck (Creative) Prepare handouts or leave-behinds (Creative) Final asset approval (Creative Lead) | T-75 |  | T-60 |  | Creative
Pre-Event | Audience Architecture | Qualification | Booth qualification criteria finalized | Define stop / pass rules (Sales Ops) Define qualifying questions (Sales Ops) Align criteria with RevOps (RevOps) Criteria approved and documented (Sales Ops) | T-75 |  | T-60 |  | Sales Ops
Pre-Event | Audience Architecture | Personas | Target personas defined | Identify priority personas (Sales) Validate personas vs event audience (Marketing Ops) Align with speaking content (Content) Final persona list approved (Sales Lead) | T-90 |  | T-75 |  | Sales
Pre-Event | Audience Architecture | Outcomes | Speaker audience outcome defined | Define what should change for the attendee (Content) Align outcome with CTA (Growth) Confirm measurability (RevOps) Outcome approved (Content Lead) | T-90 |  | T-75 |  | Content
During | Experience Design | Booth | Booth experience flow designed & trained | Define booth, hook, and opener (Sales) Define conversation flow (Sales Ops) Define CTA pitch (Partnerships) Conduct staff training & role-play (Event Ops) | T-45 |  | T-30 |  | Event Ops
During | Experience Design | Speaking | Speaking CTA & follow-up path finalized | Insert CTA into slides (Content) Test CTA link/QR (Growth Ops) Confirm verbal call-to-action (Content Lead) Final rehearsal complete (Event Lead) | T-45 |  | T-30 |  | Growth
During | Experience Design | Conversion | Meeting booking mechanism live | Configure booking tool (RevOps) Integrate with CRM (RevOps) Test live booking flow (RevOps) Confirm on-site readiness (Event Lead) | T-30 |  | T-14 |  | RevOps
Post | Experience Design | Nurture | Post-event nurture sequence activated | Define nurture stages (Lifecycle) Write follow-up emails/messages (Content) Build workflows in HubSpot (RevOps) Activate Day 1 post-event (Lifecycle) | T-30 |  | T+1 |  | Lifecycle
Pre/During | Operational Excellence | Staffing | Booth staffing & training completed | Assign booth shifts (Event Ops) Confirm staff availability (People Ops) Distribute talking points (Sales Ops) Training completion confirmed (Event Ops) | T-45 |  | T-30 |  | Event Ops
Pre-Event | Operational Excellence | Systems | Lead capture & CRM tested | Select scanning/capture tool (RevOps) Configure fields and routing (RevOps) Test live scans into CRM (RevOps) Reporting verified (RevOps Lead) | T-30 |  | T-14 |  | RevOps
Pre-Event | Operational Excellence | Coordination | Run-of-show coordination complete | Align booth + speaking schedule (Event Lead) Coordinate with host AV/ops (Event Ops) Confirm speaker timing (Content) Final run-of-show approved (Event Lead) | T-30 |  | T-14 |  | Event Lead
During | Team & Accountability | Authority | On-site owner assigned | Assign on-site decision owner (Partnerships Lead) Confirm authority scope (Event Lead) Communicate escalation path (Ops) Owner logged (Event Lead) | T-14 |  | T-7 |  | Partnerships Lead
During | Team & Accountability | Performance | Daily performance check-ins completed | Review meetings booked daily (Event Lead) Review booth traffic vs goal (Sales Ops) Adjust staffing or CTA as needed (Event Lead) Daily notes recorded (Event Lead) | T |  | T |  | Event Lead
Post | Team & Accountability | Reporting | 30/60/90-day funnel report delivered | Collect funnel data (RevOps) Analyze vs benchmarks (RevOps) Summarize learnings (Event Lead) Leadership readout delivered (Exec Sponsor) | T+1 |  | T+90 |  | RevOps